## Pramsheds Owned
Negotiations on the acquisition of the owner interest Pramsheds
Title | First Name | Surname |  |  |  | Address | New Comments 2017 | Offer Accepted or Replacement | Progress | date sold/ completed | amount sold for | Chasing letters emails calls | All letters sent | Temp Shed requested
Mr | Bina | Moosavi-Hejazi |  |  |  | 1 Granville Point |  | sold | SOLD | 9.5.17 | 3500 |  | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | Kevin | Ryan |  |  |  | 5 Granville Point |  | Accepted £3500 | emailed 3.2.17 but wrong charles so re emailed HB law 8.3.17 |  |  | 12.10.17 t/c to leaseholder to chase up returning docs, 8.1.18 phoned leaseholder and left a message. HBPL chased 3.1.18 and 8.2.18, HP spoke to mr ryan who confirmed he would collect letter Feb 18. HP 6.3.18 phoned and left message as papers were not collected. 18.4.18 HP phoned and left a message. 15.5.18 HP left message with L/H answerphone to call. 15.5.18 HP offered HBPL to hand deliver docs | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | Prakash | Kataria |  |  |  | 13 Granville Point |  | Prefers Replacement | emailed HB Law 20.2.17 to start paperwork |  |  | 12.10.17 left message on answerphone to return docs,6.11.17 emailed L/H to chase signed paperwork, h chased by email. 30.1.18 leaseholder phoned with a new address. HBPL sent new docs to new address 6.2.18, 18.4.18 HP phoned leaseholder he has been on holiday and will sign this week and return. 8.5.18 HP phoned l/h and he was looking for a witness, he will do it today and return. 15.5.18 HP phoned and left a message for L/H to call. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | M T | Rahbary |  |  |  | 14 Granville Point | phoned leasholder, he is thinking of replacment, I will send him the proposed plan, also owns 14 & 19 granville and 15 templewood - HP 1.3.17 | Accepted £3500 but now prefers replacment | HB Pulblic law in process |  |  | see notes on 15 templewood, hbpl spoke to LH and resent paperwork 18.10.17, 13.11.17 l/h emailed to say he is abroad and will return forms on 17.11.17, hbpl chased 21.11.17 and 29.2.17, 8.1.18 phoned Mr rahbary who advised he wanted to go to HBPL and sign the documents there, i gave him Telephone Number. HBPL issued new docs on 8.1.18 and chased on 7.2.18. Signed forms received by HBPL on 6.3.18. 18.4.18 forms received but needs consent from lender, hbpl chased. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Ms | S O S | Bee |  |  |  | 17 Granville Point |  | Accepted £3500 | HB Pulblic law in process | 24.11.17 | 3500 | hbpl received singed paperwork 4.10.17 | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Miss | Borka | Argirova |  |  |  | 20 Granville Point |  | Accepted £3500 | sold | 15.5.17 | 3500 | sold | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | Robert Kwabena | Kusi | Mrs | Rose Afua | Kusi | 23 Granville Point | Spoke to son on 10/02/2017 - Will call back on Monday. Spoke to again, will email decision 10/03/17. | accepted £3500 | HB public law advised 19.9.17 |  |  | reminder Letter sent 17.3.17, 22.8.17, HBPL issued paperwork 18.10.17, new documents issued to LH on 23.11.17, 8.1.18 emailed son to chase him up. Hbpl sent reminder 10.1.18, 9.2.18, hp sent email reminder 19.2.18. 19.2.18 leaseholder emailed to say did not receive them, HBPL will resend by registered post today. 18.4.18 spoke to son, father died in 2015 so death cert is required to change the docs and then resend, this has been requested.3.5.18 docs now placed in sole name and sent to Mrs K for signing. 6.6.18 HP phoned l/H no response. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | Leon | Danon |  |  |  | 25 Granville Point | Had wrong address, email over details for replacement shed. There is a restriction on the title requiring named indivuals written consent to any dispostion. | Prefers Replacement | HB public law progressing 17.7.17 |  |  | chased 3.10.17. HBPL chasing w/c 6.11.17, Dec 17 leaseholder phoned HBPL and asked for docs to be sent to a different address. HBPL sent to new address on 7.2.18, hbpl chased 6.3.18,9.4.18 via post, 17.4.18 via email. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Ms | Catherine Oyibo | Edozie |  |  |  | 37 Granville Point |  | sold | SOLD | 3.11.17 | 3500 |  | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | G S | Cummings | Mrs | J D | Cummings | 41 Granville Point | Considering sale, wants to discuss alternative shed. 31/01/17 | Accepted £3500 | sold | 22.11.17 | 3500 | reminder Letter sent 17.3.17, due to complete with HBPL Nov 17 | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mrs | Jinal | Shah | Mr | Jitendra | Shah | 43 Granville Point | Spoken to on 10/02/2017 - Didn’t receive letter - email sent to tell him details | Prefers Replacement | replacement completed | 17.1.18 |  | signed paperwork received 16.10.17, finally completed march 18 | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
| Modinat Olatundu | Oki |  |  |  | 47 Granville Point |  | accepted £3500 | referred to HB Public law on 2,10,17 |  |  | reminder Letter sent 17.3.17, 22.8.17, reminder email sent to new email address 19.9.17, emailed 2.10.17, HBPL issued docs 4.10.17, HBPL chased 21.11.17 and 29.12.17. l/h phoned hbpl on 26.1.18, discussed CPO process and docs re sent 26.1.18, hbpl chased on 27.2.18,21.3.18 and 18.4.18 | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Ms | S | Kucukbalaban |  |  |  | 55 Granville Point | Spoken to on 14/02/2017 - Didn’t receive letter, send one via email, one week to respond | Accepted £3500 | emailed HB Public law 6.3.17 |  |  | 12.10.17 left message on answerphone to return docs. 8.1.18 left message on mobile to return docs. Docs returned uncalled for to HBPL. 12.2.18 HP phoned leaseholder, she will check she has the documents and sign and return them, if can't find them will phone HP. 12.3.18 hbpl spoke to leaseholder who will be sending docs back this week. 18.4.18 hp phoned and left message. hbpl phoned l/h 4.5.18 to return docs. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
S | Nine Estates | Ltd |  |  |  | 56 Granville Point |  | Prefers Replacement | emailed hb public law 8.2.17 | 8.6.17 |  | 5.9.17- isle of mann, HBPl reissued papers on 22.9.17 with revised attestion clause, 8.1.18 papers were returned but had a missing signature sent back to l/h on 3.1.18, hbpl sent reminder on 8.2.18. HP emailed 19.2.18. leaseholder reps have confirmed that signed docs were returned end of Feb 18. 6.3.18 HP requested legal update the schedule as this should be close to completion. april 18 - lender consent required, hbpl chased on 9.4.18 | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Ms | Katya | Guy-Pratt |  |  |  | 57 Granville Point |  | Prefers Replacement | replacement completed | 9.6.17 |  |  | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
| S ESTATES | Ltd |  |  |  | 1 Harpenmead Point |  | Prefers Replacement | referred to HB Public Law on 17.7.17 |  |  | HBPL sent docs 18.10.17, resent to leaseholder on 3.1.18 as some missing. Hbpl chased on 2.3.18, hp chased HBPL on 7.3.18 8.3.18 hbpl informed leaseholder they need to complete the lender authority form, resent form on 8.3.18 | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
| Sudukar | Chittigari |  | Shirisha | Chittigari | 2 Harpenmead Point |  | Prefers Replacement | HB Pulblic law in process | 8.3.17 |  | 12.10.17 HBPL has not received paperwork, phoned LH and she returned it in August, asked HBPL to re send for signing. HBPL resent paperwork 18.10.17, HBPL waiting for info from leasehold services. HP chased Liz in BH on 12.2.18. 7.3.18 has been placed for sealing. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mrs | Usha | Lyall |  |  |  | 5 Harpenmead Point | AN feb 17 Spoke to, knew nothing about a shed, and wanted to get rid of it, very rude on the phone and difficult to speak to. 20.3.17 HP spoke to leaseholder she would like a replacment, have emailed HB Law to progress | Accepted £3500 | sold | 24.11.17 | 3500 | reminder Letter sent 17.3.17, HBPL had to resend as plan not attached 4.10.17 | 1st Letter 4th Jan 2017. 2nd Letter 16th March.
S | Estates | Ltd |  |  |  | 7 Harpenmead Point |  | Prefers Replacement | emailed HB public law 8.2.17 |  |  | HBPL - resent docs 25.9.17, Dec 17 all paperwork received so completion should be in Jan 18. 7.3.18 chased HBPL as to why not completed yet.26.2.18 hbpl sent letter to lender on charge on title. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | Jerzy | Kizny |  |  |  | 8 Harpenmead Point |  | Sold | emailed HB public law 17.1.17 | 24.10.17 | 3500 | waiting for mortgagee costs | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Ms | Catherine Oyibo | Edozie |  |  |  | 9 Harpenmead Point |  | sold | SOLD | 2016-09-01 | 3500 |  | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Ms | C T | McKnight |  |  |  | 11 Harpenmead Point |  | Prefers Replacement | emailed HB Public Law 8.2.17 |  |  | 5.9.17 - HP phoned as not returned forms to HBPL, 12.10.17 chasing t/c to return docs answer phone message. Hbpl chased 20.11.17, 9.2.18, HP chased 19.2.18, hp emailed leaseholder 7.3.18. 23.4.18 hp chased l/h. 23.5.18 hp chased leaseholder. 6.6.18 phoned leaseholder and left message to sign and return docs. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Ms | Mary Ene | Abu |  |  |  | 23 Harpenmead Point | Spoken to on 14/02/2017 - Did not accept offer | Offer too low |  |  |  | reminder Letter sent 17.3.17, 22.8.17 (will now wait to after CPO) | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Miss | Adebisi Carolan | Desalu |  |  |  | 24 Harpenmead Point |  | Prefers Replacement - changed to sale | sold | 3.11.17 | 3500 | HBPL are in process of completing, 6.11.17 HP raised request for £3500 to be paid. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Ms | Hiba | Odabashy |  |  |  | 31 Harpenmead Point |  | Accepted £3500 | sold 18.8.17 | 18.8.17 | 3500 |  | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Ms | Tania | Wantochova |  |  |  | 13 Nant Court |  | replacment completed | replacement completed | 18.7.17 |  |  | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mrs | M A | Ignatius |  |  |  | 18 Nant Court |  | Accepted £3500 | sold | 18.8.17 | 3500 |  | 1st Letter 4th Jan 2017. 2nd Letter 16th March.
Ms | K M G | Pratt |  |  |  | 21 Nant Court |  | Prefers Replacement | HB Pulblic law in process |  |  | 5.9.17 - awaiting response from Bof Scotland, agreed sherrygreen will cover the costs, hbpl wrote to l/h on 13.11.18 and 5.1.18. HBPL arranging payment to solicitors feb 18, paid march 18. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | W | Patabendige | Mrs | I | Patabendige | 24 Nant Court | Spoke to briefly - Hung up on me twice - said he wasn’t a leaseholder A.N 17/03/2017. 20.3.17 leaseholder emailed HP to complain about date of letter and the fact they are waiting for a replacment shed map. I have emailed plan over and sent apology email. HP. Sept 17 and Oct 17 numerious emails regarding wording or shed or pramshed - see files. | Prefers Replacement |  |  |  | reminder Letter sent 17.3.17, issues with storage, 18.12.17 emailed with temporary storage option, leaseholder has sent long letter back, hbpl replied 5.1.18. Leaseholder wrote in 25.1.18, reply sent 12.2.18 and letter from HBPL. Objected to CPO, further coms regarding this. HBPL issued new docs to Sol on 3.4.18 | 1st Letter 13th Jan 2017. 2nd Letter 16th March. | y
Mrs | H S | Patel | Mr | S B B | Patel | 25 Nant Court |  | Accepted £3500 | sold | 24.11.17 | 3500 |  | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mrs | Catherine | Lucey | Mr | Daniel | Lucey | 29 Nant Court |  | Accepted £3500 | HB Pulblic law in process | 23.5.18 |  | legal have no response HP left message 5.9.17, left another message 19.9.17. 12.10.17 phoned to chase, l/h sent back papers by proof of postage on 20.9.17, emailed HBPL to locate the papers. HBPL resent paperwork 18.10.17. leasehold services confirmed status of charge on lease, lis and hbpl in communication 3.1.18. 13.1.18 chased liz and hbpl to sort out consent. HBPL chased liz james on 2.3.18. 8.3.18hbpl - ds3 has been placed for sealing, leaseholders asked to provide a copy ID in preparation of completion. | 1st Let+K32+D32:N32+C32:N32+B32:N32+K32+D32:N32+A32:N32
Mr | Thomas | Mitchell | Mrs | Lilieth | Mitchell | 31 Nant Court |  | Prefers Replacement | HB Pulblic law in process |  |  | leaseholder then wanted further info about new shed, HB were chasing him, 5.9.17 temp storage issue, 18.12.17 emailed with option of storage solution. Dec 17 son emailed to confirm his parents would like the temp shed, 8.1.18 emailed hbpl to confirm. 25,1,18 emailed further information to son, 13.2.18 further email sent to son, hp emailed son timeframe on 7.3.18, hbpl chased 21.3.18. 23.4.18 HP Chased son. 23.5.18 hp chased son again | 1st Letter 13th Jan 2017. 2nd Letter 16th March. | y
Mrs | Margaret | Fadojutimi | Mr | Festus | Fadojutimi | 32 Nant Court | leaseholder emailed on 20.2.17 stating they are leaseholder, emailed back asking if they wish to accept the offer. 2.10.17 emailed again about offer.16.10.17 reminded l/h to confirm if they wish to accept. | accepted £3500 | passed to HBPL 17.10.17 |  |  | reminder Letter sent 17.3.17, 22.8.17, 2.10.17. feb 18 paper work received by hbpl, 7.3.18 hp chased HBPL for progress report. 12.3.18 hbpl confirmed it should be sealed/completed today. 23.4.18 paperwork sealed 19.3.18, lender conset letter sent 19.3.18. 24.5.18 hbpl contacted Lh about payment for lenders fee. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Ms | Y | Ismail |  |  |  | 34 Nant Court |  | sold | SOLD | 6.11.17 | 3500 |  | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | N | Zullufi | Mrs | X | Zullufi | 35 Nant Court |  | Accepted £3500 | HB Pulblic law in process |  |  | HBPL chased them on 3.7.17. HBPL chased on 20.10.17 to sign and return.,hbpl chased 21.11 and 29.12, 25.1,18. Hp emailed 19.2.18, HBPL chased 27.2.18. HP got through on mobile on 6.3.18, lh advised he hadn't received any documents asked HBPL to re send, 9.4.18 hbpl sent a chaser letter, 17.4.18 hbpl sent chaser email. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mrs | Induben | Patel |  |  |  | 37 Nant Court | WRONG MOBILE NUMBER | prefers replacement, | passed to hbpl 2.10.17 |  |  | reminder Letter sent 17.3.17, 22.8.17, 8.2.18 by hbpl. 7.3.17 HP emailed HBPL for update. May 18 HBPL confirmed that leaseholder now not sure if he wants to sign or progress was advised about CPO | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | Ben | Dishman |  |  |  | 38 Nant Court |  | Prefers Replacement | completed | 3.8.17 |  | replacement completed. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | T | Murphy |  |  |  | 39 Nant Court | kimmurphy7707@gmail.com. 10.7.17 send l/h plan of new sheds. | Prefers Replacement |  |  |  | august 17 - waiting for info about temp storage - will not sign until knows date of new shed, HP in discussion with sherrygreen about temp shed. 18.12.17 emailed with temp shed storage option, 8.1.18 chased up with another email. 25.1.18 kim murphy does not want a temp shed for 24 months wants shorter timeframe. advised that 24 months is maximum time and this could be shorter but will not know until the programme is finalised. Feb 18 spoke to brother who is joint leaseholder who wants to sell not replace, i advised him he needs to email in. HP wroteto both at end of feb 18. Put in objection for CPO. 26.3.18 hbpl sent out amended docs and letter, no response. See CPO Objection folder | 1st Letter 13th Jan 2017. 2nd Letter 16th March. | Y
Mrs | Rachel | Churchhill |  |  |  | 41 Nant Court | 20.3.17 - HP - Ms Churchill purhcased the property in 2016 but we have been writing to previous owners. Emailed on 20.3.17 to apologise and re send all letters, plus plan of new sheds. | accepted £3500 | passed to HBPL 22.8.17 |  |  | NEW ADDRESS, reminder Letter sent 17.3.17, letter and email sent 22.8.17, 5.9.17 mortgage letter, HBPL have obtained offical copies and started preparing draft docs and sent to LH 18.10.17. HBPL preparing docs. Sent out 18.1.18, March 18 docs received back, and waiting for sealing, april 18 hbpl confirmed should complete soon. May 18 keys return, HBPL advised should complete June 18. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | Mohsen | Esmaeili | Mrs | Anne | Esmaeili | 1 Templewood Point |  | Accepted £3500 | HB Pulblic law in process | 1.8.17 | 3500 | sold 1.8.17 | 1st Letter 4th Jan 2017. 2nd Letter 16th March.
Mr | Khaled Abdullah | Khaledi |  |  |  | 9 Templewood Point |  | replacement completed | HB Pulblic law in process - legal work completed no further action | 27.7.17 |  | hbpl confiirmed the client kept changing their mind, completed on a areplacment | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | Taghi | Rahbary |  |  |  | 15 Templewood Point | phoned leasholder, he is thinking of replacment, I will send him the proposed plan, also owns 14 & 19 granville - HP 1.3.17 (sent on 6.3.17) HP chased again on 20.3.17, HP called on 27.3.17 he is abroad and will call us on Monday 3.4.17 | Prefers Replacement | emailed HB public Law 4.4.17 | 14.6.18 |  | reminder Letter sent 17.3.17 and email sent to chase previous email on 20.3.17. 10.8.17 have not received docs back. I have phoned him today, just recovering from open heart surgery and will sign and return asap. 4.9.17 t/c to l/h to return docs, he said he will do today. 2.10.17 emailed l/h to chase for paperwork, end of Oct 17, TC from LH. 6.11.17, emailed leaseholder to chase for docs. 13.11.17 l/h emailed to say he is abroad and will return forms on 17.11.17, phoned 27.11.17 he will return today. hbpl chased 5.1.18, 8.1.18 phoned Mr rahbary who advised he wanted to go to HBPL and sign the documents there, i gave him Telephone Number. hbpl chased 8.2.18. 19.2.18 phoned mr Rahbary who advised he will do it today, i have advised if he doesn't sign then he could end up with nothing. 5.3.18 docs received by HP who passed to HBPL. 10.4.18 hbpl still waiting response from mortgage company. | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mrs | S | Karimi-Zanjani |  |  |  | 17 Templewood Point |  | Prefers Replacement | HB Pulblic law in process | 4.12.17 |  | HBPL received docs Oct 17, should complete Nov 17 | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
ms |  | leyla |  |  |  | 19 templewood | leaseholder at number 15 is uncle and deals with her lease. I phone mr rahbury 21.9.17 - he will call his neice in america and ask what she wants to do. 2.10.19 emailed jacky nelson for any other contacts | prefers replacement | Instructed HBPL 25.10.17 |  |  | 13.11.17 l/h uncles emailed to say he is abroad and will return forms on 17.11.17, phoned 27.11.17 he will return today, 8.1.18 phoned Mr rahbary who advised he wanted to go to HBPL and sign the documents there, i gave him Telephone Number. 5.3.18 signed docs received by HP and passed to HBPL. hbpl - need ID docs, hbpl chased 9.4.18 6.6.18 HP chased HBPL so also ask uncle to ask them for the ID
Mrs | Elizabeth | El-Shafei |  |  |  | 36 Templewood Point |  | Accepted £3500 | SOLd 18.9.17 | 15.9.17 | 3500 | payment to be raised for £3500. | 1st Letter 4th Jan 2017. 2nd Letter 16th March.
Mrs | Viyaba | Jain |  |  |  | 41 Templewood Point |  | Accepted £3500, now changed her mind and would like a replacment. | HB Pulblic law in process, uodated them in 25.10.17 to say now replacment. HBPL issued replacment docs 5.10.17, chased by HBPL 20.10.17, 21.11.17 | 19.6.18 | 3500 | waiting for mortgagee costs, hbpl waiting confirmation mortgage has been discharged (6.10) HBPL chased lender 20.10 and 21.11, 8.1.18, 21.2.18. HP asked legal if leaseholder is aware of the delay 7.3.18. 18.4.18 hbpl chasing leaseholder to sort out with solictors as mortgage not discharged. | 1st L+A47:N47etter 13th Jan 2017. 2nd Letter 16th March.
| Gateglow | Ltd |  |  |  | 47 Templewood Point |  | Accepted £3500 | SOLD | 14.8.17 | 3500 | sold August 2017 - finally completed march 18 | 1st Letter 13th Jan 2017. 2nd Letter 16th March.
Mr | Tariq | Mahmood |  |  |  | 60 Templewood Point | 1.3.17 - tried to call but constantly engaged. Tried other numbers - still no answer, voicemail left. Spoke to the first number- claimed it was the wrong number. Arshad hand delivered letter, and knocked, no answer. 28/03/17 | Prefers Replacement | HB public law emailed 18.5.17 | 5.3.18 - replacement |  | reminder Letter sent 17.3.17, 10.8.17 hb public law not received docs back, I have phoned numbers and not working, emailed him to request he returns docs. HBPL chased 3.10.17, HP chased 6.11.17, 21.11.17. 8.1.18 paperwork received and all send tfor sealing - should complete by 12.1.18. Signed docs received . | split

## Pramsheds Right to Use
RIGHT TO USE | [9 empty] | Negotiations on acquiring the right to use pramshed interests
Block & No. | Ownership of Pramshed | Resident/Non Resident Leaseholder | Title | Name | Name | Title | Name | Name | Address | Address | Address | Address | Comments | Decision | Progress | date sold | Amount | Letters | Contact
52 Harpenmead Point, Granville Road, NW2 2LL | No - but Sch 1 para 1 of lease grants right to use "one of the sheds" | Non-Resident | Mr | Ali Sabih | Bahbahani |  |  |  | 30 Charfield Court | 2 Shirland Road | Maida Vale | W9 2JN | Would like to accept however money to low, does not want a replacment. 5.12.17 spoke to customer again he has confirmed he will want more money for his shed. 3.1.18 spoke to leaseholder he may consider a replacment shed - have emailed him details, chased 8.1.18 and 13.2.18. passed to HBPL 19.2.18, hbpl sent docs to leaseholder on 21.2.18. 21.3.18 hbpl chased,17.4.18 hbpl chased | Replacment Shed |  |  |  | First Letter Sent 28th March 2017- 2nd Letter sent 11th May 2017. | 7973553201 sbestdad@gmail.com
2 Nant Court, Granville Road, NW2 2LB | No - but Sch 1 para 1 of lease grants right to use "one of the sheds" | Resident | Miss | Margot Leah | Shatz |  |  |  | 2 Nant Court | Granville Road | London | NW2 2LB | 19/05/2017 asked for replacment . Issues over storage as leaseholder is elderly. Offered temporary storage. 31.1.18 hbpl sent docs to l/h. Daughter provided a copy of power of attorney and amended docs sent to daughter. hbpl chased on 28.2.18, hp emailed daughter with the time frame on storage on 6.3.18 and another email on 7.3.18 | Replacement on templewood, as none left on Nant Court, storage issue!! |  | 19.5.18 |  | First Letter Sent 28th March 2017- 2nd Letter sent 11th May 2017. | Daughte+I7:T7r MKovalyova@coahc.org Marina
16 Nant Court, Granville Road, NW2 2LB | No - but Sch 1 para 1 of lease grants right to use "one of the sheds" | Resident | Ms | Po Mui | Cheung |  |  |  | 16 Nant Court | Granville Road | London | NW2 2LB | 18/04/17 accepted offer | Accepted offer | SOLD | 18.8.17 | 3500 | First Letter Sent 28th March 2017- 2nd Letter sent 11th May 2017. | 020 8458 5039 07977 747 225 wtradingltd@hotmail.co.uk
17 Nant Court, Granville Road, NW2 2LB | No - but Sch 1 para 1 of lease grants right to use "one of the sheds" | Resident | Mr | Ernie | Fernandez | Mrs | Genedina | Fernandez | 17 Nant Court | Granville Road | London | NW2 2LB | lHBPL advised that L/H that they need consent to remove the charge before proceeding 13.9.17, HBPL chased 23.10.17./h have insructed sols who have contact the lender. Sols stated they have chased the lender and will update in due couse - 8.12.17. sol raised queries these all responded to 26.1.18 by hbpl. HBPL chased on 28.2.18. 9.4.18 hbpl were advised that l/h refusing to instruct sols as per lenders request. | Prefers replacement on Granville Point |  |  |  | First Letter Sent 28th March 2017- 2nd Letter sent 11th May 2017. | 020 8731 6627 07983 351 295
19 Nant Court, Granville Road, NW2 2LB | No - but Sch 1 para 1 of lease grants right to use "one of the sheds" | Non-Resident | Mr | D B | Feldman |  |  | 07432605965 or dbfestates@gmail.com | 2 Paget Road | London |  | N16 5NQ | 16.5.17 - wants to sell for £5000, HP emailed to say £3500 is max amount. 14.12,17 phoned to say he will now sell for £3500. instructed HBPL 14.12.17. passed to hbpl 14.12.17, hbpl sent out docs on 19.12.17, chaser sent on 7.2.18, 7.3.18 hp chased leaseholder. 21.3.18 hbpl chased l/h. 17.4.18 hbpl chased l/h | Accepted offer |  |  |  | First Letter Sent 28th March 2017- 2nd Letter sent 11th May 2017. | 020 8809 9584 07432605965 Daylight2p@gmail.com or dbfestates@gmail.com
22 Nant Court, Granville Road, NW2 2LB | No - but Sch 1 para 1 of lease grants right to use "one of the sheds" | Non-Resident | Mr | P | Enstone |  |  |  | C/o Ms L Enstone | 44 Twisden Road | London | NW5 1DN | 5.9.17- mortgage lender needs representation, sherrygreen agreed to pay costs. HBPL contacted lh on 4.1.18. HB Pulblic law in process , hbpl sent reminders to the solicitors on 4.1.18 and 8.2.18, 7.3.18 hbpl now confirmed they in communication with solicitor. | Accepted offer | SOLD | 27.3.18 | 3500 | mortgage lender required independent legal rep. LBB will cover cost and Sherrygreen will repay. | 07540 960 934 Nada_@hotmail.co.uk
40 Nant Court, Granville Road, NW2 2LB | No - but Sch 1 para 1 of lease grants right to use "one of the sheds" | Resident | Ms | Magali Rachel | Vedrenne |  |  |  | 40 Nant Court | Granville Road | London | NW2 2LB | No Replacements left on Nant- Either accept or replacement elsewhere on the development - Email sent , will now accept at Granville Point but first on waiting list for Nant. HBPL sent docs to leaseholder on 27.7.17, 6.11.17 HP chased leaseholder for return docs, 13.11.17 L/h emailed to ask q's about new sheds.,hbpl chased l/h 12.12.17, 18.12.17, 8.2.18. Hp chased 7.3.18 by email | Prefers Replacement - However no space on Nant |  |  |  | First Letter Sent 28th March 2017- 2nd Letter sent 11th May 2017. | 07854 685 763 Magali.vedrenne@googlemail.com
23 Nant Court, Granville Road, NW2 2LB | No - but Sch 1 para 1 of lease grants right to use "one of the sheds" | non -residents | Mr | P | Charalambous |  |  |  | Top Crown Investments Ltd | Athins House, 171 Ballards Lane | London | N3 1LP | 3.1.18 - hbpl confirmed that has a shed included but we were previosuly told it didn't - letter gone to leaseholder with offer. 13.218 HP Chased with another email to solicitors, 20.2.18 Sol emailed stating will not sell for less then £18K or a shed within 40ft of entrance. 26.2.18 HP advised max amount is £3500 and gave list of what sheds are available. 6.3.18 Sol said still no, 7.3.18 HP emailed with reference to planning permission and websites etc. |  |  |  |  | first letter sent 4.1.18, reminder by email 13.2.18 | charles@topcrown.co.uk